## SGD 112-Team Schedule
Team Task List for Game Design Project -- SGD 112.xxxx (replace x's with section #)
This document should be shared with each team member so timely updates can be made as needed.
Student Names --> |  | Chad Nelson | Zac Andrews | Shelby leucie | Ahmed Suoamra | Student #5 (replace with your name)
Wednesday | 2023-09-27 | Meet with the team to plan the game design. | Meet with the team to plan the game design. | Meet with the team to plan the game design. | Meet with the team to plan the game design. |  | In each cell (when appropriate) insert a brief but specific description of what you did towards development on this day.
Thursday | 2023-09-28 | [5 empty] | Add specific deadlines in this column. Check student planner and Bb for actual due dates.
Friday | 2023-09-29 | general layout and planning | general layout and planning | general layout and planning | general layout and planning
Saturday | 2023-09-30
Sunday | 2023-10-01
Monday | 2023-10-02 | Designing level 1 |  |  | Coding of player movement
Tuesday | 2023-10-03 | Designing level 1 |  | drawing space man | Coding of player movement
Wednesday | 2023-10-04 | Designing level 1 | Creating palletes | drawing space man | Coding of shooting |  | Example: MS #1 due by . . . .
Thursday | 2023-10-05 | Working on movement bugs | Creating palletes
Friday | 2023-10-06 |  |  | Animation of space man | Coding of camera follow
Saturday | 2023-10-07 |  | Creating palletes | Redrawing spaceman to pixel | Coding of enemy movement
Sunday | 2023-10-08 |  |  |  | Coding of enemy movement
Monday | 2023-10-09 |  | redoing palletes into pixels |  | fixing jetpack and other bugs
Tuesday | 2023-10-10 |  | redoing palletes into pixels | Animating/Art | Fixing more bugs
Wednesday | 2023-10-11 | helping with coding | redoing palletes into pixels | Animating/Art | health bar code
Thursday | 2023-10-12 |  | Creating enemy sprites in pixel art |  | healthbar enemy coding
Friday | 2023-10-13 | helping with coding | Designing level 2 | Animating/Art
Saturday | 2023-10-14 |  | Designing level 2 |  | Fixing script and player movement
Sunday | 2023-10-15
Monday | 2023-10-16 |  |  |  | fixing jet pack
Tuesday | 2023-10-17 |  |  |  | improving shooting mechanics
Wednesday | 2023-10-18 | Player animations | Worked on enemy sprites
Thursday | 2023-10-19 |  | Worked on enemy sprites |  | coding menu and ui
Friday | 2023-10-20 | Worked on UI |  | Animating/Art
Saturday | 2023-10-21 | Worked on UI and player animations |  | Animating/Art | fixing bugs
Sunday | 2023-10-22 | Worked on UI and player animations | Worked on enemy sprites | Animating/Art | fixing bugs |  | Example: MS #2 (Alpha) due by . . . .
Monday | 2023-10-23 |  |  | Animating/Art | fixing bugs
Tuesday | 2023-10-24 | Worked on UI and health and bugs | Made level two and art work fo it | . | fixing bugs
Wednesday | 2023-10-25
Thursday | 2023-10-26
Friday | 2023-10-27
Saturday | 2023-10-28
Sunday | 2023-10-29 | [5 empty] | Example: MS #3 (Beta) due by . . . .